## Sheet1
ID | Story Title | Depends On | Points | Priority | As a/an [user type] | I want [functionality] | So that [value] | NFR | Definition of Done | Epic ID | Notes | Status
S0 | Example |  | 1 | Medium | Professor | to create requirements | my students understand. | Understandability | When students grok! | 0 |  | Open
S1 | Secure RFQ Link Authentication |  | 3 | High | Vendor | Receive a secure link with an encoded RFQ number and hash | Ensures only authorized users can access RFQ details securely |  |  |  |  | Open
NFR1 | Generate Secure RFQ Links |  | 5 | High | Developer | Create a script to generate BASE64 encoded RFQ links and hashes | Automates secure link generation for RFQs |  |  |  |  | Open
NFR2 | Validate RFQ Link Access |  | 8 | High | System API | Verify RFQ ID and hash before returning data | Prevents unauthorized access to RFQ information |  |  |  |  | Open
S2 | Display RFQ Details |  | 3 | High | Vendor | Enter a valid RFQ link and see RFQ details on the frontend | Provides a seamless experience for vendors |  |  |  |  | Open
S3 | Submit Quote Response |  | 5 | High | Vendor | Fill and submit a quote response (pop-up) form | Enables vendors to respond efficiently |  |  |  |  | Open
S4 | Create New Part Number |  | 5 | Medium | Vendor | Add a new part number and provide justification | Allows flexibility in quoting process |  |  |  |  | Open
S5 | Upload Quote File |  | 8 | High | Vendor | Drag and drop a PDF/Excel quote to upload | Simplifies the quote submission process |  |  |  |  | Open
NFR3 | Extract Data from Uploaded Quote |  | 13 | High | System API | Parse quote file and extract relevant details automatically | Reduces manual data entry |  |  |  |  | Open
NFR4 | Match Uploaded Quote to RFQs |  | 8 | High | System API | Find and retrieve matching RFQs for uploaded quotes | Connects vendor quotes to existing RFQs efficiently |  |  |  |  | Open
S6 | Pre-fill Quote Form from Extracted Data |  | 5 | High | Vendor | See extracted quote data auto-filled in the form | Saves time and ensures accuracy |  |  |  |  | Open
S7 | Approve Pre-filled Quote Data |  | 5 | Medium | Vendor | Review and confirm extracted quote details | Prevents incorrect submissions |  |  |  |  | Open
NFR5 | Implement FIPS-Compliant Hashing Algorithm |  | 8 | High | Developer | Select and implement a FIPS-compliant hashing algorithm | Ensures security compliance and future-proofing |  |  |  |  | Open
NFR6 | Generate Hashes for Secure Authentication |  | 5 | High | Developer | Create a hashing mechanism to authenticate RFQ requests | Strengthens security for RFQ access |  |  |  |  | Open
NFR7 | Mock API for RFQ Validation |  | 8 | High | Developer | Build a mock API to validate RFQ requests | Enables testing before full integration with Sedna Core/API |  |  |  |  | Open
NFR8 | Create a JSON File for Mock Data Storage |  | 5 | Medium | Developer | Generate a JSON file with RFQ details for API testing | Supports development and debugging of authentication process |  |  |  |  | Open
NFR9 | Implement Frontend Quote Submission Form |  | 5 | High | Developer | Develop the UI for submitting quote responses | Provides vendors an easy way to submit quotes |  |  |  |  | Open
NFR10 | Implement Frontend for RFQ Retrieval |  | 5 | High | Developer | Develop the UI to fetch and display RFQ details | Improves vendor experience in viewing RFQ details |  |  |  |  | Open
NFR11 | Develop Mock Endpoint for Quote Submission |  | 5 | High | Developer | Create an API endpoint to accept quote responses | Enables frontend-backend integration testing |  |  |  |  | Open
S8 | Display Submission Confirmation |  | 3 | Medium | Vendor | Show a confirmation message upon successful quote submission | Provides assurance that submission was successful |  |  |  |  | Open
NFR12 | Store and Retrieve Submitted Quotes |  | 8 | High | System API | Save submitted quotes and allow retrieval for review | Ensures proper record-keeping of submitted quotes |  |  |  |  | Open
NFR13 | Validate Uploaded File Format |  | 5 | Medium | System API | Ensure only supported file types (PDF/Excel) are accepted | Prevents invalid file uploads |  |  |  |  | Open
S9 | Notify User of File Upload Success/Failure |  | 3 | Medium | Vendor | Show feedback when a file is uploaded | Improves user experience |  |  |  |  | Open
S10 | Provide Sample Quotes for Testing |  | 3 | Low | Project Team | Supply sample quotes from multiple vendors | Ensures system can handle real-world quote formats |  |  |  |  | Open
NFR14 | Implement Minimal Bootstrap-Based Styling |  | 5 | Medium | Developer | Use Bootstrap for UI components | Keeps UI simple yet visually acceptable for demo |  |  |  |  | Open
NFR15 | Allow System to Use External PDF Parsing Service |  | 8 | Medium | Developer | Integrate external service for parsing PDFs | Reduces complexity and speeds up implementation |  |  |  |  | Open
S11 | Allow secure vendor onboarding |  | 5 | high | Developer | make sure vendors are who they say they are | Increases security and prevents vulnerability |  |  |  |  | Open
s12 | implement login system |  | 3 | medium | Developer | allow users to make accounts to save what work they’ve done | Improves user experience and ease of access |  |  |  |  | Open